## Sheet1
S/N | STATE | LOCATION | NUMBER OF UNITS | DELIVERY DATE | DELIVERED BY | COMMENT ON SITE READINESS | REMEDIAL ACTION | FOCAL PERSON | FOCAL PERSON PHONE | PLANNED DATE OF INSTALLATION | ACTUAL INSTALLATION | Temperature inside the UCC after at the end of Testing and commissioning | Ambient Temperature during Testing and commissioning | STATUS
1 | Kano | NW Zonal Cold Store | 1 | 2021-09-17 | Isah Onu Ibrahim | Installed |  | Pharm. Nasir Roni | 07034950095 | 2021-09-24 | 2021-09-24 | - 77°C | 23°C - 35°C | Installed
2 | Kano | Kano state Cold Store | 1 | 2021-09-17 | Isah Onu Ibrahim | Installed without challenges |  | Garba Tanko | 07063005690 | 2021-09-24 | 2021-09-24 | - 79°C | 21°C - 31°C | Installed
3 | Ogun | Ogun State Cold Store | 1 | 2021-09-19 | Omole Oluwaseun | Installed |  | Oguntade Omotola | 08034233152 | 2021-09-27 | 2021-09-27 | - 77°C | 24°C - 31°C | Installed
4 | Lagos | SW Zonal Cold store | 1 | 2021-09-20 | Omole Oluwaseun | Installed |  | Dupe Kolapo | 08035992621 | 2021-09-28 | 2021-09-29 | - 81°C | 27°C - 32°C | Installed
5 | Lagos | Lagos State Cold Store | 1 | 2021-09-20 | Omole Oluwaseun | Installed |  | Adams Mina | 07083684831 | 2021-09-28 | 2021-09-28 | - 80°C | 27°C - 29°C | Installed
6 | Oyo | Oyo State Cold Store | 1 | 2021-09-19 | Omole Oluwaseun | Installed after we replace star blocks |  | Rashidat Badmus | 08055939319 | 2021-09-24 | 2021-09-24 | - 80°C | 23°C - 35°C | Installed
7 | Benue | Benue State Cold Store | 1 | 2021-09-17 | Siyaka Sunny | Team going for Installation |  | Ukpo earnest u | 07061867104 | 2021-09-30 | 2021-09-30 | - 70°C | 31°C - 32°C | Installed
8 | Katsina | Katsina Sate Cold Store | 1 | 2021-09-18 | Isah Onu Ibrahim | Installed without challenges |  | Mohammed Ibrahim | 08022409890 | 2021-09-25 | 2021-09-25 | - 79°C | 25°C - 33°C | Installed
9 | Kaduna | Kaduna State Cold Store | 1 | 2021-09-15 | Isah Onu Ibrahim | Installed without challenges |  | Charles Hosea | 08062091290 | 2021-09-23 | 2021-09-23 | - 77°C | 24°C - 31°C | Installed
10 | Borno | Borno State Cold Store | 1 | 2021-09-20 | Isah Onu Ibrahim | Installed |  | TIJJANI M. NASIR | 08036285499 | 2021-09-27 | 2021-09-27 | - 60°C | 31°C - 32°C | Installed
11 | Delta | Delta State Cold Store | 1 | 2021-09-21 | Omole Oluwaseun | Installed |  | Adaikpoh E | 07038913504 | 2021-09-30 | 2021-09-30 | - 77°C | 31°C - 32°C | Installed
12 | Gombe | Gombe State Cold Store | 1 | 2021-09-22 | Isah Onu Ibrahim | Installed |  | Abba Kumo | 08026625299 | 2021-09-29 | 2021-09-29 | - 68°C | 21°C - 23°C | Installed
13 | Rivers | Rivers State Cold Store | 1 | 2021-09-23 | Omole Oluwaseun | Claim ready for installation |  | RICHARD William | 08038864211 | 2021-10-01 | 2021-10-01 | - 60°C | 29°C - 30°C | Installed
14 | Imo | Imo State Cold store | 1 | 2021-09-23 | Omole Oluwaseun | Installed |  | Lilian O. | 08037964654 | 2021-09-30 | 2021-09-30 | - 64°C | 31°C - 32°C | Installed
15 | Plateau | Plateau State Cold Store | 1 | 2021-09-23 | Isah Onu Ibrahim | Installed |  | DAMULAK E Dalok | 08035011788 | 2021-09-28 | 2021-09-28 | - 63°C | 24°C - 26°C | Installed
16 | Ondo | Ondo State Cold Store | 1 | 2021-09-18 | Omole Oluwaseun | Installed |  | OMOYENI Wuraola | 08067471343 | 2021-09-23 | 2021-09-23 | - 79°C | 21°C - 32°C | Installed
17 | Nasarawa | Nassarawa State Cold Store | 1 | 2021-09-17 | Siyaka Sunny | Installed |  | Obed Aya | 07068780268 | 2021-09-29 | 2021-09-29 | - 63°C | 31°C - 32°C | Installed
18 | FCT | NSCS Abuja Existing | 4 | 2021-09-14 | Oluwaseun & Isah | Installed after we provided cabling and DB |  | Otowo Onojo | 08033157043 | 2021-09-24 | 2021-09-25 | - 80°C | 20°C - 21°C | Installed
[12 empty] | - 78°C | 20°C - 23°C
[12 empty] | - 80°C | 20°C - 23°C
[12 empty] | - 79°C | 19°C - 21°C
19 | FCT | NSCS Abuja Planned | 6 | 2021-09-14 | Oluwaseun & Isah | Almost Ready | Modifications being implemented | Otowo Onojo | 08033157043 | 2021-10-04 |  |  |  | Not Installed
20 | FCT | Apo | 1 | 2021-09-15 | Isah Onu Ibrahim | UCC positioned for installation tomorrow |  | Amina Sali Usman | 08037018473 | 2021-10-01 | 2021-10-01 | - 70°C | 29°C - 30°C | Installed
GREEN IS GOOD TO GO